## Sheet1
Assignee | Task Description | Progress | Date Completed | Point Worth | Sprint
freddy-nguyen-tamu | Implement Traditional User Login System | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement User Logout Functionality | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Google OAuth Login | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Google OAuth Logout | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Remember Me Feature to Stay Logged-In for a Period of Time | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Delete Account Features | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Update Account Features | Done | 2025-10-20 | 1 | 1
freddy-nguyen-tamu | Implement Forgot Your Password Feature | Done | 2025-10-21 | 1 | 1
freddy-nguyen-tamu | Implement Email Delivery for Password Reset Feature | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Create Expense and Category model | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Implement CRUD operations for expenses | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Add expense categorization feature | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Write unit tests for Expense model and CRUD functionality | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Implement Excel upload feature using Pandas | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Write integration tests with RSpec for Excel upload and expense | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Write Cucumber feature tests for expense creation, editing, deletion, and Excel upload | Done | 2025-10-21 | 1 | 1
Venkates | [Expense Management] Ability to add new categories | Done | 2025-10-22 | 1 | 1
Venkates | [Expense Management] Ability to edit existing expenses | Done | 2025-10-22 | 1 | 1
Venkates | [Expense Management] Ability to delete expenses | Done | 2025-10-22 | 1 | 1
Amesh537 | Create Group for Shared Expenses | Done | 2025-10-23 | 1 | 1
Amesh537 | Invite Users to a Group | Done | 2025-10-23 | 1 | 1
Amesh537 | Split Expense Among Group Members | Done | 2025-10-23 | 1 | 1
Amesh537 | View Total Group Expense | Done | 2025-10-23 | 1 | 1
Amesh537 | Comment on a Group Expense | Done | 2025-10-23 | 1 | 1
Amesh537 | View All Comments in a Group Expense Thread | Done | 2025-10-23 | 1 | 1
freddy-nguyen-tamu | Implement Private Direct Messaging Button Between Two Users Regarding an Expense via Expense Page | Done | 2025-10-24 | 1 | 2
freddy-nguyen-tamu | Implement Private Direct Message System Between Two Users | Done | 2025-10-24 | 1 | 2
freddy-nguyen-tamu | Fix: Restore config/development.rb and Remove Misplaced Button in Landing Page | Done | 2025-10-27 | 1 | 2
PRADEEPPERIYASAMY | Personal expense summary | Done | 2025-10-27 | 1 | 1
PRADEEPPERIYASAMY | Summary of my group expenses | Done | 2025-10-27 | 1 | 1
PRADEEPPERIYASAMY | Expenses filtered by date | Done | 2025-10-27 | 1 | 1
PRADEEPPERIYASAMY | Expenses filtered by category | Done | 2025-10-27 | 1 | 1
PRADEEPPERIYASAMY | Recent expenses on dashboard | Done | 2025-10-27 | 1 | 1
PRADEEPPERIYASAMY | Recent group expenses | Done | 2025-10-27 | 1 | 1
Venkates | Expense dashboard | Done | 2025-10-27 | 1 | 1
freddy-nguyen-tamu | Implement a Conversation Page That Divides Contactable Users Based on Groups | Done | 2025-10-31 | 1 | 2
freddy-nguyen-tamu | Implement Multiple Expense References in Messages | Done | 2025-10-31 | 1 | 2
freddy-nguyen-tamu | Implement Group-Based Conversation System with Multi-Expense Quoting for Context | Done | 2025-10-31 | 1 | 2
PRADEEPPERIYASAMY | high-level AI summary of my spending habits | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | AI analysis of that specific widget | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | Flash messages (like "Success" or "Error") | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | Landing page | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | (Sign Up, Login, Edit Profile) to be clean, styled, and easy to use | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | Expenses pages to be clean and well-styled | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | Groups pages to be clean and well-styled | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | Conversations to look and feel like a modern messaging app | Done | 2025-11-02 | 1 | 2
PRADEEPPERIYASAMY | New Category from to be a simple, styled form | Done | 2025-11-02 | 1 | 2
freddy-nguyen-tamu | Implement Backup Functionality | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Restore Functionality | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Backup & Restore User Interface | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Backup and Restore Data System | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Handle Undefined Routes with Proper Authentication | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Edit Feature for Group-Based Expenses | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Date Autofill Feature to Expense Forms | Done | 2025-11-03 | 1 | 2
freddy-nguyen-tamu | Implement Route Handling, Expense Editing Fixes, and Date Autofill Feature | Done | 2025-11-03 | 1 | 2